## US-AC Analysis - AI Chatbot
Mightyolu.com — AI Chatbot User Story Analysis (B2B & B2C)
Jira ID | Epic | Original User Story | Refined User Story | Original AC | Expanded Acceptance Criteria | Sub-Tasks | Business Value | Questions for Mightyolu | Assumptions | Risks & Dependencies | Definition of Ready | Definition of Done | Priority | Complexity
EPIC: AI Shopping Assistant
MOU-101 | AI Shopping Assistant | As a Website Visitor I want to see a chatbot icon So that I know I can get help while I shop | As a B2C Shopper or B2B Trade Account holder I want to see a persistent AI assistant icon on every page of Mightyolu.com (storefront, product pages, checkout, and the Trade Account portal) So that I have a clear, consistent entry point to get instant help with products, orders, delivery, or bulk/wholesale enquiries at any point in my visit | - The website visitor can access a virtual assistant Scenario: The user is able to access the assistant Given I am browsing Mightyolu.com, When I am on any page, Then I can see I am able to open the AI assistant | 1: Given I am on any page of Mightyolu.com (home, category, product, cart, checkout, order history, or Trade Account dashboard), When the page loads, Then I see a chat bubble icon fixed in the bottom-right corner that does not obscure the 'Add to Basket' or checkout buttons. 2: Given the icon is visible, When I click/tap it, Then the chatbot opens in a slide-out panel without leaving the current page or losing my basket contents. 3: Given the chatbot is open, When I click close/minimise, Then it collapses back to the icon and my conversation is preserved for the remainder of the browsing session. 4: Given I am a Trade (B2B) Account holder logged into the Trade portal, When the icon renders, Then the assistant greeting and quick prompts are tailored to B2B needs (e.g., 'Request a wholesale quote', 'Check my account balance') rather than consumer prompts. 5: Given I am on a mobile device, When the icon is displayed, Then it is touch-friendly, does not overlap the sticky 'basket' bar, and the panel is full-screen on small viewports. 6: Given the chatbot service is unavailable, When I click the icon, Then I see a graceful message (e.g., 'Our assistant is temporarily unavailable — you can still reach us at inquiry@mightyolu.com or 07867986338.') rather than a blank panel. 7: Given I navigate between pages (e.g., product page to checkout), When the page changes, Then the icon remains visible and any open conversation persists across the session. 8: Given I log out or switch between a personal (B2C) account and a linked Trade (B2C/B2B) account, When the switch happens, Then the chatbot context and conversation reset to match the active account type. 9: Given accessibility requirements, When the icon is rendered, Then it has an ARIA label ('Open Mightyolu assistant'), is keyboard-navigable, and meets WCAG 2.1 AA contrast requirements. | FE: Build floating chatbot icon component with fixed positioning (MOU-102) FE: Build open/close panel animation FE: Implement responsive/full-screen behaviour on mobile FE: Add ARIA labels, keyboard navigation, focus management FE: Implement error state UI for chatbot service downtime FE: Implement session-based conversation persistence across page navigation FE: Detect account type (Guest/B2C/Trade B2B) and pass context to chatbot on open FE: Reset conversation on login/logout or account-type switch QA: Test icon visibility across storefront and Trade portal pages QA: Test open/close behaviour and basket-content preservation QA: Test mobile responsiveness and tap targets QA: Test accessibility (screen reader, keyboard) QA: Test error handling when assistant service is down QA: Test conversation reset on account-type switch | Provides a single, always-visible entry point to AI support across both the B2C storefront and the B2B Trade portal, increasing self-service adoption and reducing reliance on email/phone enquiries. As the primary touchpoint for the chatbot, its discoverability directly determines the return on the AI investment. | 1. Should Guest (not logged in) users see the same assistant as registered B2C shoppers, or a simplified version prompting sign-in for order-specific queries? 2. Does Mightyolu want a single Trade (B2B) account tier, or multiple tiers (e.g., restaurant, retailer, caterer) that should each get different quick prompts? 3. Should the icon be suppressed on the checkout/payment step to avoid distracting shoppers mid-purchase? | 1: The chatbot icon appears on all storefront pages and all Trade portal pages. 2: The icon design and panel styling follow the existing Mightyolu brand palette (to be confirmed with design). 3: The chatbot panel is a slide-out overlay, not a full-page navigation. 4: Conversation state is held client-side for the duration of the session (not persisted server-side between visits) unless the user is logged in, in which case recent order context may be reused. 5: B2C and B2B/Trade users share one chatbot instance with context-aware prompts, not two separate bots. 6: The icon is visible to all visitors regardless of login state, with reduced functionality for Guests. | 1: DEPENDENCY — Chatbot backend/API (MOU-103) must expose an authenticated 'account type' flag (Guest/B2C/Trade) for the icon to tailor its greeting. 2: UX — Icon position must be coordinated with the sticky basket/checkout bar on mobile to avoid UI collision. 3: SCOPE — Confirm whether the icon should appear during the payment/card-entry step, given PCI/UX sensitivity. 4: DESIGN — Chatbot panel visuals need to be finalised before FE build can start. | 1. Chatbot icon design finalised for all states (resting, hover, active, error) 2. Chatbot panel design approved (slide-out vs full-screen mobile) 3. Chatbot API contract available (even if mocked) including account-type context 4. Positioning confirmed relative to basket/checkout UI on mobile 5. Accessibility requirements documented 6. Story pointed and PO sign-off obtained | 1. Chatbot icon visible on all storefront and Trade portal pages 2. Click opens chatbot panel; close/minimise returns to icon 3. Responsive on desktop, tablet, and mobile 4. Error state displays when chatbot service unavailable 5. Conversation persists across page navigation within a session 6. Conversation/context resets on account-type switch or logout 7. WCAG 2.1 AA compliant (keyboard, ARIA, contrast) 8. Cross-browser tested (Chrome, Safari, Edge, Firefox) 9. Code reviewed and merged 10. QA sign-off on all acceptance criteria | HIGH | MEDIUM
EPIC: AI Shopping Assistant
MOU-102 | AI Shopping Assistant | As a Customer I want to see quick help options So that I can get common questions answered fast | As a B2C Shopper or B2B Trade Account holder I want the chatbot to open with account-aware quick-action prompts (e.g., 'Track my order', 'Request a bulk quote', 'Check delivery areas') So that I can resolve common tasks in one click instead of typing out a question or searching the site | - The user can see quick-action options when opening the assistant Scenario: The user opens the assistant and sees relevant quick actions Given I am a Customer, And I open the AI assistant, Then I see a welcome message and a set of quick-action buttons relevant to me, And when I click one I get an immediate, relevant response | 1: Given I am a B2C shopper and I open the chatbot, When it loads, Then I see quick-action prompts relevant to consumer shopping (e.g., 'Track my order', 'What's on offer this week?', 'Delivery to my postcode', 'Return an item'). 2: Given I am a logged-in Trade (B2B) Account holder and I open the chatbot, When it loads, Then I see quick-action prompts relevant to wholesale/trade needs (e.g., 'Request a bulk quote', 'Check my account balance', 'Reorder my last bulk order', 'Speak to my account manager'). 3: Given I click a quick-action prompt, When the chatbot processes it, Then it returns a relevant, personalised answer (e.g., order status with tracking link, or a bulk-pricing enquiry form) within 3 seconds. 4: Given I am a Guest (not logged in) and click an account-specific prompt (e.g., 'Track my order'), When the chatbot processes it, Then I am prompted to log in or provide an order number/email before the assistant can respond. 5: Given the chatbot cannot fulfil a quick-action request (e.g., service down), When this occurs, Then the quick-action buttons show a disabled/unavailable state, but the assistant still shares fallback contact details (inquiry@mightyolu.com / 07867986338). 6: Given I am a B2B Trade Account holder requesting a bulk quote, When I click 'Request a bulk quote', Then the assistant asks for product(s), quantity, and delivery frequency, and submits this as a structured enquiry to the trade sales team. 7: Given I am on a mobile device, When the quick-action prompts render, Then they are tap-friendly and wrap/scroll appropriately without breaking the panel layout. | FE: Build quick-action prompt component (chips/buttons) driven by account type (MOU-104) FE: Wire consumer prompts (track order, offers, delivery check, returns) FE: Wire trade prompts (bulk quote, account balance, reorder, account manager) FE: Implement login/verification prompt for Guests clicking account-specific actions FE: Implement disabled state for prompts when chatbot service unavailable FE: Responsive layout for prompt chips on mobile BE: Bulk quote request structured-capture flow feeding trade sales inbox (MOU-105) BE: Order-status lookup integration with order management system QA: Test consumer quick-actions return correct data QA: Test trade quick-actions return correct data for a Trade account QA: Test Guest flow prompts for login/order lookup QA: Test bulk quote request submission end-to-end QA: Test mobile layout of prompt chips | Speeds up resolution of the most common consumer and trade enquiries (order tracking, bulk pricing, account queries), reducing inbound phone/email volume to the small Mightyolu team and giving Trade customers — who typically need fast wholesale pricing turnaround — a self-service channel that supports repeat B2B revenue. | 1. What are the definitive quick-action prompts Mightyolu wants for B2C vs B2B customers? 2. Should 'Request a bulk quote' go straight to a human sales inbox, or should the assistant attempt to return indicative pricing from a product/price list first? 3. Is there an existing Trade Account tier/pricing system, or will bulk pricing enquiries always route to a person for now? | 1: Quick-action prompts differ by account type: Guest, B2C (logged in), and Trade/B2B. 2: Quick-action prompts are a fixed, curated list per account type (not AI-generated) for Phase 1. 3: Bulk quote requests are captured by the assistant and routed to the trade sales team; the assistant does not calculate wholesale pricing itself in Phase 1. 4: Order tracking requires the shopper to be logged in or to supply an order number/email for verification. 5: There is one chatbot instance; account type only changes which prompts and data sources it uses. | 1: DEPENDENCY — Order-status lookup requires an integration with Mightyolu's order/fulfilment system; availability and API contract to be confirmed. 2: DEPENDENCY — Bulk quote capture needs a defined destination (CRM, shared inbox, or sales tool) to route requests to. 3: SCOPE — If Mightyolu later wants tiered trade pricing (e.g., restaurant vs. retailer), the quick-action and data model will need to be extended. 4: DATA — Guest order lookups must be rate-limited/verified to prevent one shopper viewing another's order by guessing order numbers. | 1. Quick-action prompt list confirmed for Guest, B2C, and Trade account types 2. Order-status data source/API confirmed and contract available 3. Bulk quote destination (inbox/CRM) confirmed 4. Guest verification method for order lookup agreed 5. Story pointed and PO sign-off | 1. Quick-action prompts render correctly per account type 2. Each consumer prompt returns accurate, relevant data 3. Each trade prompt returns accurate, relevant data for a Trade account 4. Guest flow correctly gates account-specific prompts behind verification 5. Bulk quote requests are captured and routed successfully 6. Disabled state shown when chatbot service unavailable 7. Responsive on all viewports 8. Code reviewed and merged 9. QA sign-off on all acceptance criteria | HIGH | MEDIUM
EPIC: AI ChatBot Core
MOU-103 | AI ChatBot Core | AI Chat Bot (Parent story covering the full conversational AI backend serving both B2C and B2B customers) | As a B2C Shopper or B2B Trade Account holder I want to interact with an AI-powered chatbot that understands whether I'm shopping personally or ordering on behalf of a business, and that can answer product, order, delivery, and account questions in natural language So that I can get instant, accurate answers without waiting for a human response, whether I'm buying a few items or placing a recurring wholesale order | Sub-tasks: - BE: Platform/vendor selection and prototype (MOU-106) - BE: Product catalogue & pricing integration (MOU-107) - BE: Order management system integration (MOU-108) - BE: Customer/account (Guest, B2C, Trade) context integration (MOU-109) - BE: NLU/intent recognition setup (MOU-110) - BE: Conversation flow design x 6 areas (MOU-111-116) - BE: Conversation flow implementation x 6 areas (MOU-117-122) - BE: Documentation (MOU-123) - FE: Chatbot styling and integration (MOU-124) - FE: Chatbot API integration/config (MOU-125) | 1: Given I open the chatbot, When the interface loads, Then I see a welcome message and contextual prompt suggestions based on whether I am a Guest, B2C shopper, or Trade (B2B) account holder. 2: Given I ask a general question (e.g., 'Do you deliver to Manchester?' or 'What payment methods do you accept?'), When I send the message, Then the chatbot responds with accurate, helpful guidance within 3 seconds (answers to be supplied/approved by Mightyolu). 3: Given I ask about a product (e.g., 'Do you have fresh yam in stock?' or 'What sizes does Banga Red Palm Oil come in?'), When the chatbot processes the request, Then it retrieves current catalogue and stock information and responds accordingly, including a link to the product page. 4: Given I ask about an order (e.g., 'Where is my order?'), When the chatbot processes the request, Then it retrieves and summarises order status and expected delivery date, after verifying my identity (logged-in session or order number + email). 5: Given I am a Trade (B2B) Account holder and ask about bulk pricing or minimum order quantities, When the chatbot processes the request, Then it either returns available trade pricing information or captures the enquiry as a structured lead for the trade sales team (per MOU-102 flow), never exposing another account's pricing. 6: Given I ask to speak to a person or the chatbot cannot answer, When this occurs, Then it clearly says it cannot help further and provides Mightyolu's contact details (inquiry@mightyolu.com / 07867986338), with no live agent handover in Phase 1. 7: Given the AI service is unavailable, When I attempt to use the chatbot, Then I see a graceful error message with the same fallback contact details. 8: Given I am chatting, When the conversation progresses, Then previous messages remain visible in a scrollable history for the session, but history is not retained after a page refresh (Phase 1). 9: Given the chatbot uses account-specific data (orders, trade pricing), When I interact with it, Then responses are personalised to my account only and never expose another customer's or business's data. 10: Given I am a Trade Account holder placing a recurring order, When I ask to 'reorder my usual', Then the chatbot retrieves my last bulk order and either confirms it can be repeated or routes me to checkout/sales as appropriate. | BE: Vendor/platform evaluation (e.g., Azure Bot Service + OpenAI, or equivalent) and prototype basic Q&A flow (MOU-106) BE: Product catalogue and live stock/pricing integration (MOU-107) BE: Order management system integration for status/tracking lookups (MOU-108) BE: Account context integration distinguishing Guest, B2C, and Trade (B2B) users, including trade pricing tier if applicable (MOU-109) BE: NLU/intent recognition configuration for grocery and trade-order intents (MOU-110) BE: Conversation flow DESIGN — General queries (delivery areas, payment, opening hours) (MOU-111) BE: Conversation flow DESIGN — Product & stock enquiries (MOU-112) BE: Conversation flow DESIGN — Order tracking & status (MOU-113) BE: Conversation flow DESIGN — Returns/refunds (MOU-114) BE: Conversation flow DESIGN — Trade/bulk pricing & quotes (MOU-115) BE: Conversation flow DESIGN — Reorder / recurring trade orders (MOU-116) BE: Conversation flow IMPLEMENTATION — all 6 areas (MOU-117-122) BE: Technical documentation (MOU-123) FE: Chatbot styling — panel, message bubbles, input field, quick-action chips (MOU-124) FE: Chatbot API integration and session config (MOU-125) QA: End-to-end conversation testing across all flow areas for both B2C and B2B personas QA: Test context retrieval accuracy (correct product, order, and pricing data shown) QA: Test data isolation between customer/business accounts QA: Test error handling and fallback messaging QA: Performance testing — response time under load | The AI chatbot is the headline differentiator for Mightyolu.com's customer experience, providing 24/7 self-service for both everyday shoppers and trade/wholesale buyers. It reduces enquiry handling load on a small team, speeds up bulk-quote turnaround for B2B customers, and supports Mightyolu's growth into repeat wholesale business alongside its consumer grocery base. | 1. What AI/chatbot platform or vendor does Mightyolu want to use, and what is the provisioning timeline? 2. Does Mightyolu currently have a defined Trade/B2B account and pricing structure, or does this need to be scoped as part of this work? 3. What are the priority conversation topics for go-live — is trade/bulk pricing must-have for launch, or can it follow consumer flows in a later phase? 4. Who owns and maintains the product Q&A content the chatbot will be trained/fed on? | 1: The chatbot will not support live handover to a human agent in Phase 1. 2: The chatbot is scoped to answer questions and guide navigation; it does not place orders or take payments directly. 3: B2C and B2B/Trade customers are served by one chatbot instance, differentiated by account context, not two separate bots. 4: The 6 conversation flow areas (General, Product & Stock, Order Tracking, Returns, Trade Pricing, Reorder) cover full Phase 1 scope. 5: Trade/bulk pricing responses are either pulled from a defined trade price list or captured as a lead for the sales team — the assistant does not negotiate pricing. | 1: DEPENDENCY — Confirm and provision the chosen AI/chatbot platform before backend development can begin; this is the single biggest risk to timeline. 2: FIRST-TIME DELIVERY — This is Mightyolu's first AI chatbot implementation, which may surface unknown technical or content challenges. 3: DATA — Product catalogue, stock, and order data need reliable, up-to-date integration; stale data would produce incorrect chatbot answers. 4: SCOPE — Whether a formal Trade/B2B pricing structure exists will materially affect the complexity of the trade pricing and reorder flows. 5: CONTENT — General Q&A answers need to be supplied and kept current by Mightyolu; without this the chatbot cannot answer reliably. 6: DATA SECURITY — Chatbot will access order and account data; ensure customer data isolation and no cross-account leakage, particularly between B2C and Trade accounts. | 1. AI/chatbot platform selected and provisioned 2. Product catalogue, stock, and order system integration contracts available 3. Trade/B2B account and pricing structure confirmed (or scoped as a dependency) 4. Conversation flow designs reviewed and approved for all 6 areas 5. General Q&A content supplied by Mightyolu 6. Data security/privacy review completed for account data access 7. Prioritisation of conversation flows agreed (must-have vs. nice-to-have for go-live) 8. Story pointed and PO sign-off | 1. Chatbot configured and running against the chosen platform 2. All 6 conversation flows designed, implemented, and documented 3. Chatbot retrieves correct product, order, and account-specific data 4. Frontend chatbot panel connected end-to-end 5. Welcome message and contextual prompts display correctly per account type 6. Graceful error handling when the AI service is unavailable 7. Conversation persists across page navigation within a session 8. No data leakage between customer or trade accounts 9. Response time under 3 seconds for standard queries 10. Technical documentation completed 11. End-to-end QA across all flows for both B2C and B2B personas 12. Code reviewed and merged 13. PO acceptance of conversation quality | CRITICAL | VERY HIGH